## Launch Dashboard
WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL
WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL | WINGMAN — LIVE SUPPLY CONTROL
Launch metric | Current | Required | Status
Research-confirmed upcoming events | 34 | Live discovery inventory | PASS
Wingman-bookable events | 0 | > 0 with approved terms | FAIL
Real recruitment leads | 10 | Recruit continuously | PASS
Verified Wingmen | 0 | 3 | FAIL
Minimum supply gate | FAIL | 3 verified Wingmen | FAIL
Public launch decision | NOT READY | All gates pass | NOT READY
OPERATING RULE | OPERATING RULE | OPERATING RULE | OPERATING RULE | OPERATING RULE | OPERATING RULE | OPERATING RULE | OPERATING RULE
Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage.
Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage.
Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage. | Events may appear as discovery listings when confirmed by an official source. A ‘Book with Wingman’ action stays disabled until a verified Wingman or venue partner supplies approved inventory, pricing, terms and response coverage.
NEXT ACTIONS | NEXT ACTIONS | NEXT ACTIONS | NEXT ACTIONS | NEXT ACTIONS | NEXT ACTIONS | NEXT ACTIONS | NEXT ACTIONS
1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers.
1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers.
1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers.
1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers.
1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers. | 1. Publish the 34 confirmed events as discovery-only listings. 2. Contact the ten recruitment leads and send the same Wingman application. 3. Verify identity, consent, venue authority, inventory and payout details. 4. Assign at least three verified Wingmen and link approved offers to events. 5. Enable request/quote/payment only for those approved offers.

## Event Inventory
Event ID | Event Name | Venue | Event Date | Start Time | Area | Category | Age | Source Status | Wingman Coverage | Booking Status | Last Verified | Official Source | Available Services | Internal Notes
EVT-0001 | Peewee at E11EVEN | E11EVEN Miami | 2026-09-01 | Check source | Downtown Miami | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Discovery can be public; Wingman booking remains disabled until inventory is approved.
EVT-0002 | LDW ft Roxy Ferrari | E11EVEN Miami | 2026-09-02 | Check source | Downtown Miami | Labor Day Weekend | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0003 | LDW ft K Gianni | E11EVEN Miami | 2026-09-03 | Check source | Downtown Miami | Labor Day Weekend | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0004 | LDW ft Rick Ross | E11EVEN Miami | 2026-09-04 | Check source | Downtown Miami | Hip-hop / LDW | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0005 | LDW ft 50 Cent | E11EVEN Miami | 2026-09-05 | Check source | Downtown Miami | Hip-hop / LDW | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0006 | LDW ft Twinsick | E11EVEN Miami | 2026-09-06 | Check source | Downtown Miami | Electronic / LDW | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0007 | Labor Day ft Damaged Goods | E11EVEN Miami | 2026-09-07 | Check source | Downtown Miami | Labor Day | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0008 | Shift at E11EVEN | E11EVEN Miami | 2026-09-11 | Check source | Downtown Miami | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0009 | Borgeous at E11EVEN | E11EVEN Miami | 2026-09-12 | Check source | Downtown Miami | Electronic | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0010 | Vice at E11EVEN | E11EVEN Miami | 2026-09-18 | Check source | Downtown Miami | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0011 | DJ Pee Wee at E11EVEN | E11EVEN Miami | 2026-09-19 | Check source | Downtown Miami | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0012 | Afrojack at E11EVEN | E11EVEN Miami | 2026-09-25 | Check source | Downtown Miami | Electronic | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0013 | Ruckus at E11EVEN | E11EVEN Miami | 2026-09-26 | Check source | Downtown Miami | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.11miami.com/events | Tickets; VIP table request | Official event confirmed.
EVT-0014 | Mentirosa Thursday | LIV Nightclub | 2026-09-03 | 11:30 PM | Miami Beach | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0015 | Fetty Wap | LIV Nightclub | 2026-09-04 | 11:30 PM | Miami Beach | Hip-hop | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0016 | Disco Lines | LIV Nightclub | 2026-09-05 | 11:30 PM | Miami Beach | Electronic | 21+ | Official venue event page | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/event/EVE112156200020260905/disco-lines/ | Tickets; VIP tables | Official event page confirms date, time and age.
EVT-0017 | Lil Baby | LIV Nightclub | 2026-09-06 | 11:30 PM | Miami Beach | Hip-hop | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0018 | Mentirosa Thursday | LIV Nightclub | 2026-09-10 | 11:30 PM | Miami Beach | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0019 | Soulja Boy | LIV Nightclub | 2026-09-11 | 11:30 PM | Miami Beach | Hip-hop | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0020 | LIV on Sunday | LIV Nightclub | 2026-09-13 | 11:30 PM | Miami Beach | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0021 | Korolova | LIV Nightclub | 2026-09-18 | 11:30 PM | Miami Beach | Electronic | 21+ | Official venue event page | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/event/EVE112156200020260918/korolova/ | Tickets; VIP tables | Official event page confirms date, time and age.
EVT-0022 | Matroda | LIV Nightclub | 2026-09-19 | 11:30 PM | Miami Beach | Electronic | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0023 | LIV on Sunday | LIV Nightclub | 2026-09-20 | 11:30 PM | Miami Beach | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0024 | Steve Aoki | LIV Nightclub | 2026-09-25 | 11:30 PM | Miami Beach | Electronic | 21+ | Official venue event page | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/event/EVE112156200020260925/steve-aoki/ | Tickets; VIP tables | Official event page confirms date and VIP tables.
EVT-0025 | Crankdat | LIV Nightclub | 2026-09-26 | 11:30 PM | Miami Beach | Electronic | 21+ | Official venue event page | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/event/EVE112156200020260926/crankdat/ | Tickets; VIP tables | Official event page confirms date, time and age.
EVT-0026 | LIV on Sunday | LIV Nightclub | 2026-09-27 | 11:30 PM | Miami Beach | Nightclub | 21+ | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.livnightclub.com/miami/events/ | Tickets; VIP tables | Official event confirmed.
EVT-0027 | ISOxo & Brutalismus 3000 | Factory Town | 2026-09-05 | Check ticket page | Hialeah / Miami | Electronic | Check source | Official ticketing partner | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://dice.fm/venue/factory-town-noal | Tickets | Event appears on Factory Town's DICE venue page; reconfirm before publication.
EVT-0028 | Sara Landry | Factory Town | 2026-09-06 | 10:00 PM | Hialeah / Miami | Electronic | 18+ | Official ticketing partner | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://dice.fm/event/q2pyby-sara-landry-6th-sep-factory-town-miami-tickets | Tickets | DICE event page confirms date, time, venue and age.
EVT-0029 | Kaskade: ORIGIN // | Factory Town | 2026-09-18 | 10:00 PM | Hialeah / Miami | Electronic | 18+ | Official venue event page | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.factorytown.com/event/kaskade-2026-09-18-miami-fl/ | Tickets | Official venue page confirms 10 PM–5 AM and 18+.
EVT-0030 | BLOOM | M2 Miami | 2026-09-04 | Check source | Miami Beach | Nightclub / dance | Check source | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.m2miami.com/ | Tickets; VIP tables | Official venue calendar confirms event name and date.
EVT-0031 | Alegria | M2 Miami | 2026-09-06 | Check source | Miami Beach | Nightclub / dance | Check source | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.m2miami.com/ | Tickets; VIP tables | Official venue calendar confirms event name and date.
EVT-0032 | Industry Sessions | M2 Miami | 2026-09-07 | Check source | Miami Beach | Nightclub / dance | Check source | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.m2miami.com/ | Tickets; VIP tables | Official venue calendar confirms event name and date.
EVT-0033 | Friday Night in The Back Room | M2 Miami | 2026-09-11 | Check source | Miami Beach | Nightclub / dance | Check source | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.m2miami.com/ | Tickets; VIP tables | Official venue calendar confirms event name and date.
EVT-0034 | Daxson | M2 Miami | 2026-09-12 | Check source | Miami Beach | Electronic | Check source | Official venue calendar | Unassigned | Awaiting Wingman inventory | 2026-08-31 | https://www.m2miami.com/ | Tickets; VIP tables | Official venue calendar confirms event name and date.

## Wingman Pipeline
Lead ID | Organization / Person | Lead Type | Public Source | Public Contact Method | Likely Coverage | Profile Consent | Identity Check | Venue Authority Evidence | Agreement Signed | Verification Status | Production Visible | Owner | Next Action | Internal Notes
WM-LEAD-001 | E11EVEN VIP Services | Venue VIP team | https://www.11miami.com/table-reservations | tables@11miami.com ¦ 305-829-2911 | E11EVEN tables and VIP service | No | Not started | Not requested | No | Not contacted | No | Avneet | Request a partnership call and authorized host introductions | Real organization; not yet a Wingman partner.
WM-LEAD-002 | LIV Miami VIP / Events Team | Venue VIP team | https://www.livnightclub.com/miami/faq/ | Official venue contact and booking pages | LIV tickets and VIP tables | No | Not started | Not requested | No | Not contacted | No | Avneet | Request partnership contact and approved inventory process | Do not rely on older third-party promoter details.
WM-LEAD-003 | Club Space Partnerships | Venue partnership team | https://www.clubspace.com/clubshows | partnerships@clubspace.com | Club Space and related shows | No | Not started | Not requested | No | Not contacted | No | Avneet | Ask for partner inventory and authorized host referral | Venue lead; not an individual Wingman.
WM-LEAD-004 | M2 Miami VIP Team | Venue VIP team | https://www.m2miami.com/ | Official venue website | M2 events and VIP tables | No | Not started | Not requested | No | Not contacted | No | Avneet | Request an authorized VIP host contact | Venue lead; no consent or inventory yet.
WM-LEAD-005 | Factory Town Special Events | Venue partnership team | https://www.factorytown.com/ | Official venue special-events contact | Factory Town events | No | Not started | Not requested | No | Not contacted | No | Avneet | Ask for approved event and hospitality contact | Venue lead; tickets do not equal Wingman inventory.
WM-LEAD-006 | VIP South Beach | Nightlife reservations business | https://www.vipsouthbeach.com/south-beach-miami-nightclub-promoters-reservations/ | info@vipsouthbeach.com ¦ 305-804-5071 | South Beach nightlife reservations | No | Not started | Not requested | No | Not contacted | No | Avneet | Invite business owner or authorized hosts to apply | Public business contact; verify legal entity and venue authority.
WM-LEAD-007 | Best Miami Clubs | VIP reservations business | https://www.bestmiamiclubs.com/contact | tables@bestmiamiclubs.com ¦ 305-980-9556 | Miami Beach tables | No | Not started | Not requested | No | Not contacted | No | Avneet | Invite an authorized representative to apply | Public business contact; claims require verification.
WM-LEAD-008 | Azul Privé | Luxury concierge business | https://azulprive.com/miami-nightlife-vip | Official website contact | LIV, E11EVEN and other Miami VIP requests | No | Not started | Not requested | No | Not contacted | No | Avneet | Request partnership and supporting venue authority | Public concierge business; advertised access is not independently verified.
WM-LEAD-009 | Miami Promoter DK | Independent public host lead | https://www.instagram.com/miamipromoter_dk/ | Public Instagram profile | Guest lists and table reservations | No | Not started | Not requested | No | Not contacted | No | Avneet | Send application link; verify identity and venue relationships | Do not copy profile photos or publish without written consent.
WM-LEAD-010 | Promo James | Independent public host lead | https://www.instagram.com/promojames/ | Public Instagram profile | Miami experience and day-club promotion | No | Not started | Not requested | No | Not contacted | No | Avneet | Send application link; verify identity and venue relationships | Do not copy profile photos or publish without written consent.

## Verification Checklist
Gate | Requirement | Evidence Required | Public Field? | Blocking? | Owner | Status | Notes
Consent | Written permission to create and display profile | Signed agreement or timestamped digital consent | No | Yes | Avneet | Not started | Never copy a public profile into production without consent.
Identity | Legal identity matches applicant | Government ID plus approved identity check | No | Yes | Operations | Not started | Store sensitive documents securely; never expose them publicly.
Contact | Phone and email verified | Completed verification challenge | No | Yes | Operations | Not started
Venue authority | Can legitimately quote or fulfill stated access | Venue email, contract, roster or manager confirmation | No | Yes | Partnerships | Not started | Public social claims are insufficient.
Inventory | Real availability and terms | Approved event/table offer with timestamp | No | Yes | Partnerships | Not started | Must include minimum spend, fees and expiry.
Profile | Accurate bio, areas, specialties and response time | Applicant-approved profile copy | Yes | Yes | Operations | Not started | Only approved media with usage rights.
Payout | Recipient and tax/payment details verified | Approved payout record | No | Yes | Finance | Not started | Payout identity must match agreement.
Policies | Accepts cancellations, refunds and conduct rules | Policy acknowledgement | No | Yes | Operations | Not started
Training | Can operate request, quote, chat and escalation flow | Completed test booking | No | Yes | Operations | Not started
Quality | Response and fulfillment test passed | Operator-reviewed trial request | No | Yes | Operations | Not started | Publish expected response window only after testing.

## Import Schema
Entity | Field | Type | Required | Public? | Source | Rule / Meaning
events | event_id | text | Yes | No | Wingman | Stable internal identifier
events | name | text | Yes | Yes | Official event source | Exact published event name
events | venue_id | relation | Yes | Yes | Wingman venues | Must resolve to a verified venue record
events | starts_at | datetime | Yes | Yes | Official source | Store UTC plus venue timezone
events | age_requirement | text | Yes | Yes | Official source | Show ‘check source’ when not confirmed
events | official_source_url | url | Yes | Yes | Official source | Supports audit and customer verification
events | source_verified_at | datetime | Yes | No | Wingman operator | Refresh before expiry or major date change
events | discovery_status | enum | Yes | Yes | Wingman operator | draft ¦ discovery_ready ¦ cancelled ¦ expired
wingmen | wingman_id | text | Yes | No | Wingman | Stable internal identifier
wingmen | display_name | text | Yes | Yes | Applicant approved | Never inferred from public pages
wingmen | verification_status | enum | Yes | Yes | Wingman operations | pending ¦ verified ¦ paused ¦ rejected
wingmen | areas | array | Yes | Yes | Applicant approved | Miami areas served
wingmen | specialties | array | Yes | Yes | Applicant approved | Venue/vibe/occasion specialties
wingmen | response_window_minutes | number | Yes | Yes | Measured and approved | Do not publish an untested SLA
wingmen | media | array | Yes | Yes | Rights-cleared upload | Applicant owns or licenses each image
offers | offer_id | text | Yes | No | Wingman | Stable internal identifier
offers | event_id | relation | Yes | No | Event Inventory | Links offer to real event
offers | wingman_id | relation | Yes | Yes | Verified Wingman | Only verified Wingmen may own offers
offers | service_type | enum | Yes | Yes | Approved inventory | guest_list ¦ ticket ¦ vip_table ¦ concierge
offers | minimum_spend | currency | Conditional | Yes | Approved inventory | Required for minimum-spend offers
offers | service_fee | currency | Yes | Yes | Wingman pricing | Disclose before acceptance
offers | terms | text | Yes | Yes | Partner approved | Arrival, party size, cancellation and venue rules
offers | expires_at | datetime | Yes | No | Partner approved | Prevents stale inventory
offers | bookable | boolean | Yes | Yes | System | True only when every supply gate passes